## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to AI Contract Compilance Checker, compilance in GDPR and HIPAA jurisdiction | MUST HAVE | No dependency | Reddi Thanuja | 3- Completed
S1 | S1 | US-001 | Automatic identification of the key clauses in contracts | MUST HAVE | NLP | Reddi Thanuja | 3- Completed
S2 | S2 | US-001 | Risk analysis based on extracted clauses | MUST HAVE | Risk engine | Reddi Thanuja | 3- Completed
S2 | S2 | US-001 | Suggest modifications to contracts based on detected risks | SHOULD HAVE | Clause analysis | Reddi Thanuja | 3- Completed
S3 | S3 | US-001 | Implement multi-platform integration | MUST HAVE | Backend | Reddi Thanuja | 3- Completed
S3 | S3 | US-001 | Add real-time pop up notifications on the website | MUST HAVE | Frontend | Reddi Thanuja | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 31 | 6 | 7 | 7 | 4 | 2 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to AI Contract Compilance checker | 2025-10-10 | 2025-10-12 | Reddi Thanuja | Design | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Automatic identification of key clauses | 2025-10-13 | 2025-10-16 | Reddi Thanuja | Coding | 3-Completed | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Risk analysis based on extracted clauses | 2025-10-17 | 2025-10-24 | Reddi Thanuja | Coding | 3-Completed | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Suggest modifications based on detected risks | 2025-10-25 | 2025-11-01 | Reddi Thanuja | AI/ML | 3-Completed | 6 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Implement multi-platform integration | 2025-11-02 | 2025-11-06 | Reddi Thanuja | Integration | 3-Completed | 5 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Add real-time pop up notifications on the website | 2025-11-07 | 2025-11-12 | Reddi Thanuja | Backend | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Document parsing accuracy issues | Implemented OCR prepocessing for scanned documents
Sprint 1 | Day 5 | Compilance rule conflicts in complex contracts | Created rule priority hierarchy system
Sprint 2 | Day 8 | Risk scoring algorithms giving inconsistent results | Calibrated scoring weights with expert inputs
Sprint 2 | Day 15 | Report generation performance issues | implemented background job processing
Sprint 3 | Day 20 | UI inconsistency across platforms | Applied responsive design fixes
Sprint 3 | Day 26 | Pop-up notifications not triggering | Fixed event handlers for stable notifications

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-10-10 | 2025-10-16 | Thanuja,Kavya,Ruchika,Hariharan | Start improving document parsing accuracy | Stop relying on basic preprocessing methods | Continue structured clause extraction development | Added OCR preprocessing for better document handling
2 | Sprint 2 | 2025-10-17 | 2025-11-01 | Thanuja,Kavya,Ruchika,Hariharan | Start refining risk scoring logic | Stop using outdated rule checks | Continue validating clause analysis outputs | Tuned scoring weights and added background processing
3 | Sprint 3 | 2025-11-02 | 2025-11-12 | Thanuja,Kavya,Ruchika,Hariharan | Start enhancing cross-platform UI consistency | Stop manual testing of notification triggers | Continue strong frontend-backend coordination | Fixed responsive issues and stabilized real-time notifications
4
5
6
7